## effort
Date | Effort [h] | Additional Effort [h]
2012-09-12 |  | 2.5 | Specification of RTuinOS API
2012-09-15 | 6 |  | C code of scheduler core
2012-09-17 | 3.5 |  | Configuration of gcc, how to combine assembly and C code, example contextSwitch
2012-09-18 | 3.5 | 2 | Concept prove "contextSwitch" pu to operation
2012-09-19 | 2 |  | contextSwitch cleaned up, permanent context switches succeed
2012-09-20 | 3 | 1 | Review of helper program timer2Irq, code templates for Arduino
2012-09-21 | 5 | 1 | Continuation of implementation rtos.c. First compilable revision, which is "running" with 0 tasks defined. No suspend operations so far
2012-09-22 | 5.25 |  | Continuation of implementation rtos.c. Implementation problems with first suspend operation; New implementation concept made but not proven or implemented yet
2012-09-24 | 1.5 | 1 | First suspend is running. TC02: Idle is periodically interrupted by a single task and then continued
2012-09-25 |  | 1
2012-09-26 | 2.5 |  | waitForEvent, setEvent implemented. TC03 added, but does not yet run
2012-09-27 | 3 |  | Debugging of current implementation. Still no success with two tasks plus idle
2012-09-28 | 4 |  | First success with two tasks plus idle but not yet proven by profound testing
2012-10-01 | 2 |  | First non-trivial test cases are running well
2012-10-02 | 5.5 |  | Doxygen set up, setEvent completed and first related, new test case tc05 succeeds
2012-10-03 | 2.25 |  | Implementation task overrun and stack usage, not tested yet
2012-10-04 | 2 | 2 | Implementation application interrupts, not tested yet. Testing of setEvent/waitForEvent
2012-10-05 | 2 |  | Code cleanup check of all test cases as preparation of re-implementation index->pointer
2012-10-06 | 3.25 |  | Redesign of implementation of core using pointers to task objects
2012-10-08 | 1 |  | Manual set up from LaTeX template
2012-10-10 | 2 |  | Implementation of Round-Robin. GNU FDL added to manual
2012-10-11 | 2.25 |  | Manual continued
2012-10-12 | 5 |  | Manual continued
2012-10-15 | 2.5 |  | Fix: Bad specification of ALL events - now timer events are still an OR condition. Implementation of waitForEventsTillTime by generalization of waitForEvent
2012-10-16 | 2.5 |  | Code cleanup, suspendTillTime discarded. Implementation of enter/leaveCriticalSection
2012-10-17 | 1.75 |  | Manual continued
2012-10-18 | 1.75 |  | Manual continued
2012-10-23 | 2.5 |  | Manual continued
2012-10-24 | 2.75 |  | Manual continued
2012-10-25 | 2.5 | 1.25 | Makefile: Dependency files incorporated, Manual continued
2012-10-26 | 4 |  | Manual continued, widely completed as draft but without chapter Use Cases
2012-10-30 | 2.75 | 2 | Manual continued
2012-10-31 | 2.75 |  | Manual reviewed
2012-11-01 | 1.5 |  | Manual reviewed
2012-11-05 | 1 |  | Manual continued
2012-11-06 | 2 |  | Manual continued, new test case tc07
2012-11-07 | 2.25 | 0.75 | Creation of installer, test case tc07 put to operation
2012-11-08 | 3 |  | Installer creation scripts continued, missing readMe files added
2012-11-12 | 3.5 |  | Installer creation scripts continued, new test case tc08
2012-11-14 | 2.5 |  | Test case tc08 put to operation but still shows some bad behavior
2012-11-15 | 2.5 |  | Test case tc08 is working well, a fix of rtos.c was required. All test cases rerun. Manual updated
2012-11-16 | 3.25 |  | Preparation of release, new test case tc09
2012-11-19 | 1.25 |  | Makefile: Workaround for 12 Bit Branch distance problem with core.a