## effort
Date | Effort [h] | Additional Effort [h] | Task
2013-05-29 | 2.5 | 2.5 | Revision of Makefile
2013-05-30 | 2 |  | Documentation Makefile changes. Concept for new sync objects
2013-05-31 | 2 |  | Concept of new sync objects
2013-06-01 | 0.75 |  | Design of implementation new sync objects
2013-06-05 | 2 |  | Implementation of mutexes
2013-06-06 | 2 |  | Implementation of mutexes
2013-06-07 | 2 | 2 | Update Manual
2013-06-07 | 2.25 |  | Implementation of mutexes
2013-06-10 | 2 |  | Implementation of mutexes: Basically done. No test case implemented yet, no testing done yet
2013-06-11 | 1.5 |  | Implementation of tc11_mutex