## effort
Date | Effort [h] | Additional Effort [h]
2012-09-12 |  | 2.5 | Specification of RTuinOS API
2012-09-15 | 6 |  | C code of scheduler core
2012-09-17 | 3.5 |  | Configuration of gcc, how to combine assembly and C code, example contextSwitch
2012-09-18 | 3.5 | 2 | Concept prove "contextSwitch" pu to operation
2012-09-19 | 2 |  | contextSwitch cleaned up, permanent context switches succeed
2012-09-20 | 3 | 1 | Review of helper program timer2Irq, code templates for Arduino
2012-09-21 | 5 | 1 | Continuation of implementation rtos.c. First compilable revision, which is "running" with 0 tasks defined. No suspend operations so far
2012-09-22 | 5.25 |  | Continuation of implementation rtos.c. Implementation problems with first suspend operation; New implementation concept made but not proven or implemented yet
2012-09-24 | 1.5 | 1 | First suspend is running. TC02: Idle is periodically interrupted by a single task and then continued
2012-09-25 |  | 1
2012-09-26 | 2.5 |  | waitForEvent, setEvent implemented. TC03 added, but does not yet run
2012-09-27 | 3 |  | Debugging of current implementation. Still no success with two tasks plus idle
2012-09-28 | 3.75 | 0.25 | First success with two tasks plus idle but not yet proven by profound testing
2012-10-01 | 2 |  | First non-trivial test cases are running well
2012-10-02 | 5 | 0.5 | Doxygen set up, setEvent completed and first related, new test case tc05 succeeds
2012-10-03 | 2.25 |  | Implementation task overrun and stack usage, not tested yet
2012-10-04 | 2 | 2 | Implementation application interrupts, not tested yet. Testing of setEvent/waitForEvent
2012-10-05 | 2 |  | Code cleanup check of all test cases as preparation of re-implementation index->pointer
2012-10-06 | 3.25 |  | Redesign of implementation of core using pointers to task objects